## ADI Log
Date Logged | Date/Setting of Occurrence | Statement | Action, Decision, or Issue? | Responsible/Affected Party | Outcome

## Risk Register
Date Logged | Description of Risk | Impact Description | Impact Level | Probability Level | Priority Level | Mitigation Notes | Owner
2023-10-26 | Not all members answering email | Members could miss out on time-sensitive info. | 4 | 4 | 16 | Send follow-up texts via mobile phone. | PgM
2023-12-09 | No-Show: Self-Development and Life Skills Pilot Group Session | Self development and life skills pilot group session was a no-show from coordinator on December 8, 2023. PgM did not receive any prior communication from coordinator about potential absence from session. | 5 | 4 | 20 | Monitor closely for follow up and or response against official start of SCMP. 12/9: First written warning sent via email and text message to Octavia. 12/12: Text message sent to Gigi (ED) alerting of risk (no response since right before Dec 8 pilot session. | PgM

## Lessons Learned Register
Date Logged | Date of Occurrence | Statement | Responsible/Affected Party | Outcome | Lesson
2023-10-29 | 2023-10-24 | The Exec Director posted some pilot activities in the GroupMe, but because it was muted, the PgM almost missed this. This causes a rush to especially connect with the Self-Care Coord, as she has only this week to prepare for her pilot activity (D-Day: 03 NOV). | PgM, SCMP Coordinators | Late start on SCMP activites because of tentative assignments and start dates | Pay attention to all of the communications channels for Esi's House.
2023-10-29 | 2023-10-24 | PgM reached out to the Exec Director to confirm resources - which ones have already been picked by her and which ones are pending. | SCMP Staff | Assigned resources are knowing their roles a bit late but were asked to confirm via email. | Confirm from the start what resources are already assigned and which ones are not.