## SCMP
Communication Title | Audience | Vehicle of Communicaiton | Frequency | Medium | Source | Delivered by | Sensitivities | Date Delivered | Expected Result
SCMP Kickoff meeting | SCMP Program Personnel | Formal Meeting | Once (at start of program) | Presentation | N/A | Program Manager | N/A | 2023-11-18 | Bring all staff together and intitiate the SCMP program - review overaching goals, initiatives, roles, regulations, and trainings.
Onboarding: Mentor Goal Planning meeting | PgM and Case Manager Optional: Support Services Coordinator | One-on-one Informal Meeting | Once every month | Virtual | N/A | Program Manager | N/A | TBD | First Meeting: Identify individual overall goals for each participant in the following areas: self development, parenting, education and career, & financial literacy. Subsequent Meetings: Review & adjust as needed.
Mentoring Progress meeting | PgM and Mentor Optional: Case Manager | One-on-one Informal Meeting | Once every month | Virtual | N/A | Program Manager | N/A | TBD | Check in with each mentor (preferably at the beginning of the month), identify risks/issues/solutions, and relay general progress. Highlight notable progress and provide assistance, as needed.
Coordinator Progress meeting | Director of Training/Curriculum Development and Coordinator Optional: PgM, Case Manager | One-on-one Informal Meeting | Once every month | Virtual | N/A | Director, Training/Curriculum Development | N/A | TBD | Check in with each Coordinator (preferably at the beginning of the month), identify risks/issues/solutions, and relay general progress. Highlight notable progress and provide assistance, as needed.
Program Staff Check-In | PgM, Coordinators, and Mentors Optional: Case Manager and Support Services Coordinator | Formal Meeting | Once every quarter | Virtual | N/A | Program Manager | N/A | TBD | Check in with all program staff, identify risks/issues/solutions, and relay general progress. Highlight notable progress. Quarterly status reports will be collected from each Mentor.
Quarterly Mentoring Status Report | PgM and Mentor | Status Report | Once every quarter | Email | N/A | Mentor | N/A | TBD | Quarterly status report is comprised of the 3 monthly mentoring status reports. These will be submitted to PgM at Program Staff Check-In and will be submitted to Case Manager, Supportive Services Coordinator, and Executive Director for review.
Mentor and Mentee | One-on-one meeting | Informal Meeting | Biweekly | Virtual | N/A | Mentor | N/A | TBD | Center of SCMP: 1:1 sessions between mentor & mentee to initiate rapport and progress toward mentee's goals. Highlight notable progress and provide assistance, as needed.
Mentoring Status Report | PgM, Case Manager, and Mentor | Status Report | Once every month | Email | N/A | Mentor | N/A | TBD | Status report from mentor will relay progress from mentoring sessions to Case Manager and PgM. These status reports will inform the Mentor Goal Planning meetings (above - Line 3).
Initial Mentee Assessment | PgM, Case Manager, and Mentor | Status Report | Once (at start of program) | Email | N/A | Mentor | N/A | TBD | Mentor initiates contact with mentee and hosts initial meeting. The detailed outcome of this meeting will be relayed through this status report.
Self Development and Life Skills | Coordinator, mentees | Group meeting | Once every month | Virtual | N/A | Coordinator | N/A | TBD | Lead the group in a self-development & life skills activity.
Self Development and Life Skills | Coordinator, mentee | One-on-one meeting | Biweekly | Virtual | N/A | Coordinator | N/A | TBD | Coach the mentee in matters pertaining to self-development & life skills. Develop a 1 year SMART goal for each pillar, and help the mentee to break down that goal into manageable monthly and weekly goals.
Self-Care | Coordinator, mentees | Group meeting | Once every month | In-person | N/A | Coordinator | N/A | 01 Nov 2023 & after | Engage the group in a self-care activity (i.e., Girls' Night Out).
Career and Education Development | Coordinator, mentee | One-on-one meeting | Once every month | Virtual | N/A | Coordinator | N/A | TBD | Coach the mentee in matters pertaining to career and education development. Develop a 1 year SMART goal for each pillar, and help the mentee to break down that goal into manageable monthly and weekly goals.
Financial Literacy | Coordinator, mentees | Group meeting | Once every month | Virtual | N/A | Coordinator | N/A | TBD | Coach group in a matters pertaining to financial literacy.
Financial Literacy | Coordinator, mentee | One-on-one meeting | Once every month | Virtual | N/A | Coordinator | N/A | TBD | Coach the mentee in matters pertaining to financial literacy. Develop a 1 year SMART goal for each pillar, and help the mentee to break down that goal into manageable monthly and weekly goals.
Parenting Support | Coordinator, mentees | Group meeting | Once every month | In-person | N/A | Coordinator | N/A | 01 Nov 2023 & after | Lead the group in matters pertaining to parenting and relevant support.
Parenting Support | Coordinator, mentee | One-on-one meeting | Once every month | Virtual | N/A | Coordinator | N/A | TBD | Coach the mentee in matters pertaining to parenting skills. Develop a 1 year SMART goal for each pillar, and help the mentee to break down that goal into manageable monthly and weekly goals.

## Sheet1
Compatibility Report for Esis_SCMP_Communication Plan.xls
Run on 10/23/2023 13:51
If the workbook is saved in an earlier file format or opened in an earlier version of Microsoft Excel, the listed features will not be available.
Minor loss of fidelity | # of occurrences | Version
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 3 | Excel 97-2003